# Implementation workplan

Project Title:

Team Members:

Name

Project goals:

Goal

Last Updated: dd/mm/yyyy

| - Implementation stage (Plan, do, sustain) | - Activity | - Deliverable | - Notes/considerations | - Start date | - End date | - Most responsible person | - Required resources | - Status (Not started, in progress, complete) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - List what stage of implementation your activity relates to. | - Identify specific tasks, strategies, or actions you will take to accomplish your goal. | - Define the outcome or result expected from the activity. | - Include any insight or contextual details relevant to each activity. | - dd/mm/yyyy | - dd/mm/yyyy | - Name | - List any necessary tools, personnel, or budget items to support the activity. | - Change the status to reflect where the activity is at. |

# Implementation workplan: Example

Project Title: Launch of new agency intake program

Team Members:

Manager of Clinical Services (Implementation lead)

Intake Worker

Child and Youth Mental Health and Addictions Clinicians

Communications Coordinator

Youth Advisor

Project Goals:

All staff use a standardized approach to intake and referrals within the agency.

Increase awareness of programs and services.

Increase accessibility to programs and services.

Decrease wait times.

LAST UPDATED: 15/06/2024

| - Activity | - Deliverable | - Notes/considerations | - Start date | - End date | - Most responsible person | - Required resources | - Status (Not started, in progress, complete) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| - Identify specific tasks, strategies, or actions you will take to accomplish your goal. | - Define the outcome or result expected from the activity. | - Include any insight or contextual details relevant to each activity. | - dd/mm/yyyy | - dd/mm/yyyy | - Name | - List any necessary tools, personnel, or budget items to support the activity. | - Change the status to reflect where the activity is at. |
| - Plan |  |  |  |  |  |  |  |
| - Identify and build the capacity of champions. | - Key people within the agency have the knowledge and skills to support staff to facilitate change. | - Consider people closely aligned with this work – Intake Workers and clinicians. - Work with champions to develop a shared understanding of what a champion entails and the support they need to do this role well. |  |  | - Manager of Clinical Services | Staff time |  |
| - Create resources to support the intake process. | - A standardized approach to intake has been outlined, and materials have been developed to support training and implementation. | - Consider different audiences and formats needed when creating resources. - Think through which partners (e.g. staff, young people) must co-develop specific resources. - Develop a communications plan. |  |  | - Manager of Clinical Services | Staff time Resource development budget (i.e. printing) |  |
| - Do |  |  |  |  |  |  |  |
| - Host staff town hall. | - An all-staff meeting has been hosted. The new program has been introduced, and time was provided for questions and answers. | - Work to message how this will impact staff and clients – visual and succinct. |  |  | - Executive Director |  |  |
| - Provide training to all clinical staff. | - All necessary staff members have been trained. | - Identify which staff members are required to complete training. Work with these staff and managers to ensure proper timing and accessibility. - Ensure champions are co-facilitating the training. |  |  | - Manager of Clinical Services | Staff time Meeting space Training materials |  |
| - Sustain |  |  |  |  |  |  |  |
| - Hold implementation team evaluation meeting. | - Analyze, interpret, and report on data findings. - Determine the effectiveness of the new intake process. |  |  |  | - Manager of Clinical Services |  |  |